# Falcon Staffing Plan

This staffing plan shows the roles and monthly allocation for the Falcon team from March to December 2026. It was first drafted on 20 February 2026 and revised on 18 September 2026 for the Phase 2 roles that start on 21 September 2026.

## Allocation by month (full-time equivalent)

| Role | Mar-Jul | Aug-Sep | Oct-Nov | Dec |
| --- | --- | --- | --- | --- |
| Executive sponsor | 0.1 | 0.1 | 0.1 | 0.1 |
| Project lead | 0.8 | 0.6 | 0.8 | 0.5 |
| Delivery lead | 1.0 | 0.8 | 1.0 | 0.5 |
| Engineering | 2.5 | 1.5 | 3.0 | 1.0 |
| Data analyst | 1.0 | 0.5 | 1.0 | 0.5 |
| Designer | 0.5 | 0.3 | 0.5 | 0.2 |
| Quality analyst | 0.5 | 0.3 | 1.0 | 0.3 |

## Phase 2 roles

Engineering: ingestion, search and question answering, and the warehouse migration

Data analyst: search quality measurement and the evaluation question set

Designer: pilot feedback and refinements to the interface

Quality analyst: test plan, user acceptance testing and defect triage

Project lead and delivery lead: plan, budget tracking and steering reporting

## Notes

Aug-Sep reflects the reduced bridge-period team under Change Order 02. Allocation in December supports the pilot closing report and handover. Dollar amounts by role are held in the finance files, not in this plan.