## Slide 1
Falcon Phase 1 Executive Readout
12 August 2026 - Harborview Platform for Brightwater Logistics
Fictional demo content

## Slide 2
Phase 1 Outcomes
• Search live across six source libraries with nightly refresh
• Tagging live on 2,400 documents with 87 percent reviewer acceptance
• CRM records searchable through the connector added in Change Order 01
• Security review closed with no open findings
Fictional demo content

## Slide 3
Financial Summary
• Phase 1 SOW $31,500 plus Change Order 01 of $6,800
• Phase 1 total: $38,300, delivered on budget
• Change Order 02 funds a bridge period at no added fee
Fictional demo content

## Slide 4
Delivery Summary
• Eight sprints from 20 April to 7 August: 96 of 108 stories completed
• Remaining stories moved to the bridge period
• Phase 1 ended on 7 August 2026
Fictional demo content

## Slide 5
Lessons Learned
• Split large integration stories early
• Share demo builds with the client before each demo
• Agree document freshness ownership with the client
Fictional demo content

## Slide 6
Phase 2 Proposal
• Add question answering (Ask) over approved documents
• Extend to teammate documents with owner download
• Pilot Ask with two client teams
• Budget to be requested: $48,200
Fictional demo content

## Slide 7
Decisions Requested
• Endorse the Phase 2 proposal for the steering committee
• Confirm the bridge period plan for Sprints 9 to 11
• Name a client owner for document freshness
Fictional demo content