## Slide 1
Falcon Sprint 10 Demo
Sprint 10: 24 August to 4 September 2026 - demo held 4 September 2026 during the bridge period
Fictional demo content

## Slide 2
Sprint Goal
• Show the first question answering prototype
• Keep search quality steady while the team is reduced
• Prepare evidence for the Phase 2 budget decision
Fictional demo content

## Slide 3
Bridge Period Context
• Change Order 02 funds Sprints 9 to 11 at no added fee
• Funded from Phase 1 contingency
• Team of three keeps the platform running and builds the Ask prototype
Fictional demo content

## Slide 4
What We Delivered
• Ask prototype answers questions from one library with cited sources
• Retention view for stale documents released
• Document owner shown on every result
• 9 of 10 committed stories completed
Fictional demo content

## Slide 5
Live Demo Flow
• Ask a policy question and open the cited passage
• Show an answer that says no source was found
• Compare the answer with the keyword search result
Fictional demo content

## Slide 6
Feedback and Risks
• Client delivery lead wants answers limited to approved sources
• Response time varies on long documents
• Pilot team selection still open
Fictional demo content

## Slide 7
Next Steps
• Sprint 11 starts 7 September: steering pre-read and budget request
• Steering committee on 14 September to decide Phase 2
• Phase 2 would start 21 September if approved
Fictional demo content