## Slide 1
Falcon Phase 2 Kickoff
Brightwater Logistics - kickoff on 21 September 2026, deck updated 18 September 2026
Fictional demo content

## Slide 2
Where We Are
• Phase 1 ended on 7 August 2026 and was reviewed at the readout on 12 August 2026
• The bridge period covered Sprints 9 to 11 (10 August to 18 September 2026)
• Search, ingestion and question answering work for the Phase 1 document set
Fictional demo content

## Slide 3
Approved Budget
• The steering committee approved the Phase 2 budget of $48,200 on 14 September 2026
• The budget is not-to-exceed; any increase needs a signed change order
• Budget tracked monthly and reported to the steering committee
Fictional demo content

## Slide 4
Phase 2 Objectives
• Improve search quality against an agreed set of test questions
• Let a team ask questions across documents its teammates share
• Migrate the warehouse document store, planned for early November
• Run a pilot with two client teams
Fictional demo content

## Slide 5
Sprint Plan
• Sprint 12: 21 September to 2 October 2026: kickoff, backlog and quality baseline
• Sprint 13: 5 to 16 October 2026: question answering across shared documents
• Sprint 14: 19 to 30 October 2026 - goal: pilot Ask for two teams
Fictional demo content

## Slide 6
Pilot
• Pilot with two teams runs 9 to 27 November 2026
• Client names the two teams and releases time for training
• Closing report and handover follow in December
Fictional demo content

## Slide 7
Risks to Watch
• Warehouse migration timing and data quality
• Pilot team availability around the November period
• Search quality on older scanned documents
Fictional demo content

## Slide 8
Next Steps
• Sprint 12 planning on the kickoff day
• Client to confirm pilot teams by the end of Sprint 12
• First Phase 2 steering update in October
Fictional demo content