# Falcon Steering Committee Minutes - 14 September 2026

Minutes of the Falcon steering committee meeting held on 14 September 2026. The committee approved the Phase 2 budget of $48,200, set the Phase 2 kickoff for 21 September 2026, changed the steering cadence and recorded actions for the start of Phase 2 of the Harborview Platform for Brightwater Logistics.

## Attendees

| Role | Attendance |
| --- | --- |
| Executive sponsor | Present (chair) |
| Client sponsor | Present |
| Client delivery lead | Present |
| Project lead (User 1) | Present |
| Delivery lead (User 2) | Present |
| Finance business partner | Present |

## Decisions

Phase 2 budget of $48,200 approved on 14 September 2026, unanimously.

Phase 2 kickoff, and the start of Sprint 12: 21 September to 2 October 2026, confirmed for 21 September 2026.

Monthly steering meetings move to the first Monday of each month, starting 5 October 2026.

A contingency of 5 percent of the approved budget is held by the Executive sponsor and released only with written approval.

## Context

The Phase 1 total was $38,300. The bridge period (Sprints 9 to 11) ran at no added fee under Change Order 02 and closes on 18 September 2026. The Finance business partner confirmed that Phase 1 invoices are reconciled and that the Phase 2 budget is funded for the full period.

## Risks noted

Warehouse system cutover is planned for early November and depends on the data migration rehearsal.

Pilot teams for Ask must be named by the Client sponsor by the end of September.

## Actions

| ID | Action | Owner | Due |
| --- | --- | --- | --- |
| A-31 | Sign the Phase 2 Statement of Work | Client sponsor | 16 September 2026 |
| A-32 | Issue the Phase 2 kickoff invitation | Project lead (User 1) | 16 September 2026 |
| A-33 | Name two pilot teams | Client sponsor | 30 September 2026 |
| A-34 | Set up contingency approval route | Finance business partner | 25 September 2026 |