# Change Order 02 - Bridge Period

Change Order 02, dated 3 August 2026, funds a bridge period for Falcon covering Sprints 9 to 11 (10 August to 18 September 2026), between the end of Phase 1 and the start of Phase 2. It carries no added fee and is paid from the Phase 1 contingency.

## Reason for the change

Phase 1 ends on 7 August 2026, but the Phase 2 budget will not be decided until the steering committee meets in September. Stopping would lose the team and the momentum, so both parties agreed to keep a reduced team working on low-risk items.

## Work in the bridge period

Sprint 9: 10 to 21 August 2026: stabilise ingestion and fix open Phase 1 defects

Sprint 10: 24 August to 4 September 2026: improve search ranking and show it in the Sprint 10 demo

Sprint 11: 7 to 18 September 2026: prepare the Phase 2 plan, backlog and budget request

## Funding

No additional fee is charged. The effort is drawn from the Phase 1 contingency, so the Phase 1 total stays at $38,300. Hours above the contingency are absorbed by the firm.

## What does not change

Terms of the Master Services Agreement

Acceptance of Phase 1 deliverables

The rule that new scope needs a written change order

## Approval

Approved by the client sponsor and the executive sponsor on 3 August 2026.