## Slide 1
Falcon Delivery Roadmap
Phases and milestones for the Harborview Platform - revised 16 September 2026
Fictional demo content

## Slide 2
Roadmap at a Glance
• Phase 1: 2 March to 7 August 2026, discovery and core build
• Bridge period: 10 August to 18 September 2026, Sprints 9 to 11
• Phase 2: 21 September to 30 October 2026 build, then pilot in November
Fictional demo content

## Slide 3
Phase 1 Milestones
• 2 March: kickoff; 12 February statement of work signed for $31,500
• 20 April: Sprint 1 starts, eight sprints to 7 August
• 11 May: Change Order 01 approved, Phase 1 total $38,300
• 12 August: executive readout of Phase 1
Fictional demo content

## Slide 4
Bridge Period
• Change Order 02 on 3 August 2026 funds Sprints 9 to 11 from contingency
• Sprint 10 demo on 4 September shows improved search ranking
• Phase 2 plan and budget request prepared in Sprint 11
Fictional demo content

## Slide 5
Phase 2 Milestones
• 14 September 2026: steering committee approves $48,200
• 21 September 2026: kickoff and Sprint 12 start
• Sprint 14: 19 to 30 October 2026: pilot Ask for two teams
• Early November: warehouse cutover (planned)
Fictional demo content

## Slide 6
Pilot and Close
• Pilot with two teams: 9 to 27 November 2026
• Training and handover to the client support team during October and November
• Closing report in December 2026
Fictional demo content

## Slide 7
Dependencies
• Pilot teams named by the client by the end of Sprint 12
• Warehouse system owner confirms the migration window
• Search quality target agreed before the pilot starts
Fictional demo content