## Slide 1
Falcon Phase 1 Kickoff
Brightwater Logistics - kickoff meeting, 2 March 2026
Fictional demo content

## Slide 2
Why We Are Here
• Staff lose time searching for documents across several repositories
• Phase 1 builds the first working version of the Harborview Platform
• The statement of work was signed on 12 February 2026
Fictional demo content

## Slide 3
Objectives
• Complete discovery and agree the priority use cases by early April
• Build search and question answering in eight two-week sprints from 20 April
• Hold a Phase 1 readout and recommend next steps in August
Fictional demo content

## Slide 4
Scope and Fee
• Fixed fee of $31,500 covering five deliverables, D1 to D5
• CRM integration is excluded and would need a change order
• Changes to scope are agreed in writing by both sponsors
Fictional demo content

## Slide 5
Team and Roles
• Executive sponsor and client sponsor own decisions and escalations
• Project lead owns plan, risks and the budget
• Delivery lead owns sprints, quality and the technical approach
• Client delivery lead owns access, users and review of deliverables
Fictional demo content

## Slide 6
Ways of Working
• Weekly delivery meeting and written status note each Friday
• Monthly steering committee, first meeting in April
• Risks and decisions logged in shared files visible to the client
Fictional demo content

## Slide 7
First 30 Days
• Repository access granted by the client within two weeks
• Stakeholder interviews and a discovery workshop
• Current-state assessment and findings report drafted
• Environment set up and security review started
Fictional demo content

## Slide 8
Questions and Next Steps
• Confirm the meeting calendar and steering dates
• Client delivery lead to send the repository access list
Fictional demo content