# Falcon Steering Committee Minutes - 15 June 2026

Minutes of the Falcon steering committee meeting held on 15 June 2026, the mid-Phase 1 review for Brightwater Logistics. The meeting reviewed progress against the Phase 1 plan, confirmed that Change Order 01 (CRM integration, approved 11 May 2026) is in effect, discussed risks and recorded decisions and actions.

## Attendees

| Role | Attendance |
| --- | --- |
| Executive sponsor | Present (chair) |
| Client sponsor | Present |
| Client delivery lead | Present |
| Project lead (User 1) | Present |
| Delivery lead (User 2) | Present |
| Finance business partner | Present |

## Progress

Phase 1 (SOW value $31,500, plus $6,800 from Change Order 01, total $38,300) is on budget with 44 percent of funds consumed.

Sprint 5: 15 to 26 June 2026 started today; Sprints 1 to 4 delivered 31 of 36 committed stories.

Nightly ingest of the shared drive is running for four of six source libraries.

The CRM connector (CO01) passed its first read-only test on 9 June against the sandbox.

## Risks discussed

R-04 Source permissions: two libraries have inconsistent access lists. Owner: Client delivery lead.

R-07 Search relevance on scanned PDFs is below target. Owner: Delivery lead (User 2).

R-09 Sandbox availability for the CRM system is limited to weekdays. Owner: Project lead (User 1).

## Decisions

Continue with the current Phase 1 scope; no further scope changes are expected in Phase 1 delivery.

Scanned PDFs will be handled by an OCR pass in Sprint 7 rather than excluded.

The next steering meeting is set for July at the Executive sponsor's discretion.

## Actions

| ID | Action | Owner | Due |
| --- | --- | --- | --- |
| A-21 | Reconcile access lists for the two libraries | Client delivery lead | 26 June 2026 |
| A-22 | Publish OCR approach note | Delivery lead (User 2) | 3 July 2026 |
| A-23 | Confirm sandbox hours with CRM vendor | Project lead (User 1) | 22 June 2026 |
| A-24 | Circulate finance summary | Finance business partner | 19 June 2026 |