# Forecast vs Actual - Q3 2026

This document compares Falcon actual spend for Q3 2026 (July to September) with the forecast, and restates the Phase 2 forecast by role against the approved budget of $48,200. Prepared by the Delivery lead (User 2), created 5 October and revised 9 October 2026, for the Finance business partner and the Client sponsor.

## Q3 actuals against forecast

| Month | Scope | Forecast | Actual | Variance |
| --- | --- | --- | --- | --- |
| July | Phase 1, Sprints 7 and 8 | $18,600 | $18,700 | +$100 |
| August | Phase 1 close-out and bridge | $13,400 | $13,150 | -$250 |
| September | Bridge and Phase 2 start | $15,900 | $15,700 | -$200 |
| Q3 total |  | $47,900 | $47,550 | -$350 |

Q3 closed $350 under forecast. Phase 1 stayed within the $38,300 total ($31,500 signed 12 February 2026, plus $6,800 for Change Order 01), and the bridge period used less contingency than planned.

## Phase 2 forecast by role

Spend to 2 October covers only the last days of September. The forecast at completion is unchanged from the approved budget.

| Role | Approved budget | Spent to 2 Oct | Forecast at completion | Variance |
| --- | --- | --- | --- | --- |
| Engineering | $26,400 | $4,550 | $26,400 | 0 |
| Data | $9,800 | $1,700 | $9,800 | 0 |
| Design | $5,200 | $1,400 | $5,200 | 0 |
| Project management | $4,300 | $800 | $4,300 | 0 |
| Quality assurance | $2,500 | $300 | $2,500 | 0 |
| Total | $48,200 | $8,750 | $48,200 | 0 |

## Variance commentary

Engineering ($26,400) is $150 ahead of the September plan; October carries the heaviest load for the Ask pilot, so no saving is assumed.

Data ($9,800) is $100 under for September and the warehouse quality checks are still forecast at the planned effort.

Design ($5,200), project management ($4,300) and quality assurance ($2,500) are on plan.

## Risks to the forecast

A slip in the warehouse cutover would move data and quality assurance effort into November. Any resulting overspend would be raised as a contingency request to the steering committee; no request has been made.