# Data Migration Plan - Warehouse Cutover

This plan covers the migration of the client's warehouse data into the Harborview Platform ingest store for Falcon Phase 2, revised on 14 October 2026. The warehouse cutover is 2 November 2026. The plan sets out the steps, owners, the parallel run, the rollback approach and the 98.5 percent data quality threshold.

## Cutover

Cutover is planned for 2 November 2026, a Monday, ahead of the pilot window of 9 to 27 November 2026. A parallel run of five working days precedes it, with the legacy extract and the new ingest producing output side by side.

## Data quality threshold

A migration batch passes when at least 98.5 percent of rows pass row-level checks (mandatory fields, key uniqueness, referential integrity and date validity). The threshold was agreed on 29 September 2026. Rows that fail are quarantined, counted and reported; they are not loaded.

## Steps and owners

| Step | Description | Owner | Planned |
| --- | --- | --- | --- |
| M1 | Dry run on a copy of the warehouse | Engineers | Complete |
| M2 | Row-level check rules reviewed | Analysts | Complete |
| M3 | Parallel run, five working days | Engineers and analysts | 26 to 30 October |
| M4 | Go or no-go review | Delivery lead (User 2) and Client delivery lead | 30 October |
| M5 | Cutover and reconciliation | Engineers | 2 November |
| M6 | Post-cutover check | Analysts | 3 to 4 November |

## Rollback

Trigger: pass rate under the threshold, or a severity 1 defect on the cutover day.

Action: stop ingest, repoint consumers to the legacy extract, keep the new store for analysis.

Decision owner: Delivery lead (User 2), with the client delivery lead informed within one hour.

Risks and dependencies are tracked in the project risk register.